Appendix 2

To the RA Government Decree N---L, dated 2020

2020-2022 ACTION PLAN

FOR THE IMPLEMENTATION OF POLICE REFORM STRATEGY

| Direction: The profile of the new Police Objective: Changing the image of a state body that applies coercion measures and services the incumbent power into one that serves the public, is a trustworthy state service that deserves respect. Target: Increased confidence in the Police service․ Public opinion poll: The Baseline in 2019 was 4.4, according to the Global Competitiveness Index of the World Economic Forum, and the target for 2023 is set to be at least 6. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| N | Action | Target as Scheduled |  |  |  |  |  | Responsible agency |  |  | Outcome/ Verifiable Indicators | Source of Funding |  |  |  |  |  |  |  |  |  |
|  |  | 2020 |  | 2021 | 2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Audit of the vocational education programs and state educational indicators of the Police Educational Complex | Second semester |  |  |  |  |  | RA Ministry of Justice RA Ministry of Education, Science, Culture and Sports |  |  | The conclusion of the audit, including recommendations on follow-up measures, has been submitted to the Prime Minister’s Staff. Baseline 0; 2022 1 | Funding is not required. |  |  |  |  |  |  |  |  |  |
| 2 | Revision of current vocational educational programs and state education indicators |  |  | First semester Second semester |  |  |  | RA Ministry of Justice RA Ministry of Education, Science, Culture and Sports RA Ministry of Finance |  |  | Revised programs and national education indicators have been approved. Baseline 0, in 2022 at least 30% By-laws have been amended and approved. Baseline 0 In 2020 for Patrol Service in end 2022 all others | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 3 | Reforming education environment | Second semester |  | Second s semester | First semester |  |  | RA Ministry of Justice RA Ministry of Education, Science, Culture and Sports RA Ministry of Finance |  |  | The environment at the Police Educational Complex have been aligned with the ideological vectors of the new Police by means of the redesign of the educational and other areas of the complex. in 2021 new shooting range, 4 pilot auditoriums | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 4. | Recruitment of teaching staff to apply modern methodology in teaching the new educational programs | First semester |  | First semester |  |  |  | RA Ministry of Justice RA Ministry of Finance |  |  | The procedure of recruitment of teaching staff has been approved Baseline 0; in 2022 1 At least 10 teachers have been selected for teaching patrol education programs Baseline 0; In 2022 - 1 | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 5 | Conducting training for police leadership | Second semester |  | First semester | First semester |  |  | RA Ministry of Justice |  |  | Training programme has been approved Baseline 0; In 2022 1 The trainings have been conducted Baseline 0; In 2022 70% of the leadership | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 6. | Improving the remuneration and social guarantees of police officers |  |  | Second semester | First semester |  |  | RA Ministry of Finance |  |  | The situational analysis of remuneration and social guarantees of police officers has been submitted to the to the Prime Minister’s Staff. Based on the results of the study, proposals within the framework of the annual budget allocations of the Police have been submitted | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| Direction: Legal and structural model of the Police Problem: A structure that ensures a low level of effectiveness (*Translator’s Note: Due to its polysemantic nature, the Armenian word «խնդիր» seems to have been interpreted differently throughout the document as either “objective” or “problem”, hence the inconsistency in the English translation.) Target: A responsible body that has been granted political responsibility and functions of developing and implementing sectoral policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law. |
| 1 | Conducting studies to assess the effectiveness of the structural units of the Police | Second semester |  |  |  |  |  | RA Ministry of Justice RA Ministry of Finance | The study has been conducted, recommendations have been submitted to the Prime minister’s Staff. |  |  |  | Funding is not required. |  |  |  |  |  |  |  |  |
| 2 | Audit of the current functions of the Police | Second semester |  |  |  |  |  | RA Ministry of Justice RA Ministry of Finance | The audit has separated main policing functions per se from those of supporting nature; repetitions have been revealed |  |  |  | Funding is not required. |  |  |  |  |  |  |  |  |
| 3. | Establishment of a new ministry based on the Police and Migration Services | Second semester | First semester Second semester |  |  |  |  | RA Ministry of Justice RA Ministry of territorial administration and infrastructure RA Ministry of Finance | The package of draft laws related to the structure and activities of the government has been submitted to the Prime Minister's Office The Charter and the Structure of the new Ministry a have been approved The Ministry of Internal Affairs has been created and operational; an area for the Ministry has been ensured, [vacant] positions have been filled Baseline 0; in 2022 70% of the staff administration is recruited, the space for facility is allocated. |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law |  |  |  |  |  |  |  |  |
| Direction: Introduction of the Patrol Police Service and Operative Management Center Problem: Inefficient use of external services of police and its resources Target: Establishment of external police service –the patrol police, that deserves respect Basic: such service doesn’t exist Target: 2021 First semester in Yerevan 2022 First semester throughout the country |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Amending the Law on Police, the Law on Police Service Liquidation of units with duplicating functions, repealing legal acts | First semester |  |  |  |  |  | RA Ministry of Justice RA Ministry of Finance | The legal basis for the formation of the patrol police service has been established; following pubic discussion, the draft legislative package has been submitted to the Prime Minister's Office. Proposed amendments have been discussed and adopted Baseline 0; In 2020 30% of suggested amendments |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |
| 2. | Revision of other by-laws to approve the Charter and Structure of Patrol service and approval of the rules of employment of the new service. | First and second semesters |  |  |  |  |  | RA Ministry of Justice | Charter and Structure of Patrol service have been approved. Relevant by-laws have been adopted. Baseline 0; In 2022-1 |  |  |  | Funding is not required. |  |  |  |  |  |  |  |  |
| 3. | Adoption of state indicators for vocational education to award with ''Patrol-officer'' degree on ''Policing'' specialty. | Second semester |  |  |  |  |  | RA Ministry of Justice RA Ministry of Education, Science, Culture and Sports | The state indicators for vocational education to award with ''Patrol-officer'' degree on ''Policing'' specialty has been approved Baseline 0; In 2022 - 1 |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law |  |  |  |  |  |  |  |  |
| 4 | Organization of education of patrol officers | Second s semester | First and Second semesters |  |  |  | First semester | RA Ministry of Justice RA Ministry of Finance | 600 servants are trained up in 2021first six-month period 1200 servants are trained up in 2022first six-month period of 1500 servants are trained up in 2022 second six-month period of |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |
| 5 | Phase-by-phase launch of the Patrol Service |  | First semester |  |  |  |  | RA Ministry of Justice RA Ministry of Finance | In Yerevan in 2020 first six-month period of In Lori and Shirak in 2021 second six-month period of Throughout the country in 2022 first six-month period of |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law |  |  |  |  |  |  |  |  |
|  | 5.1 Ensuring logistics of Patrol Service | First and Second semesters | First and Second semesters |  |  |  |  |  | In 2021first six-month period the patrol cars, patrol officers in Yerevan, are provided with necessary equipment and uniforms In 2022 first six-month period Patrol Service throughout the RA; logistics is ensured |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5.2 Ensuring building facilities for Patrol service | First and second semesters | First and Second semesters |  |  |  |  |  | In 2021first six-month period the Patrol Service is fully operational in Yerevan and has appropriate technically equipped space |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. | Audit of current IT systems and necessary networks | Second semester |  |  |  |  |  | RA Ministry of Justice RA Ministry of High-Tech Industry | The audit of current IT systems and necessary networks have been finalised, the results have been submitted to the RA Prime-Minister’s staff. |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law |  |  |  |  |  |  |  |  |
| 7 | Phase-by-phase launch of Operations Management Centre (OMC) | Second semester | First semester |  |  |  |  | RA Ministry of Justice RA Ministry of Finance Ministry of High-Tech Industry RA Ministry of Emergency Situations RA Ministry of Healthcare | The [Republican] OMC in Yerevan, including technical and software support has been launched, specialists have been trained Baseline 0; Yerevan (Republican) OMC in 2020; territorial OMCs in all marzes in 2020 Amendments have been made to the Law on Police and the Law on Police Service. The Charter of Police, including the provisions on its structure has been changed; likewise the Charter of the Patrol Police Service has been adopted. |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law |  |  |  |  |  |  |  |  |
| 8 | Launch of Operations Management Center in marzes |  | First and second semesters |  |  |  | First and second semesters | RA Ministry of Justice RA Ministry of Finance Ministry of High-Tech Industry RA Ministry of Emergency Situations RA Ministry of Healthcare | The territorial Operations Management Centres in all marzes, including technical and software support have been launched, specialists have been trained-up Baseline 0; In 2022 the OMC is operational in all marzes Baseline 0; In 2022 60% of OMC staff is employed |  |  |  | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |
| Direction: Demilitarization of Police troops, public order protection Problem: Uncertainty about the status of Police troops, practical engagement and employment of the troops Target: Ensuring specialized Police troops under civilian oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Development of legislative drafts package on repealing the Law on Police Troops and amending the Law on Police |  |  | First semester |  |  |  | RA Ministry of Justice RA Ministry of Defense |  |  | Public discussions on the legislative drafts package on repealing the Law on Police Troops and amending the Law on Police have been conducted, recommendations accepted Baseline 0 In 2021 at least1 public discussion conducted, 30% of recommendations accepted The legislative drafts have been submitted to the Prime Minister’s Staff. | Funding is not required. |  |  |  |  |  |  |  |  |  |
| 2 | Audit of the number of servants fulfilling functions, reserved for Police troops. | Second semester |  |  |  |  |  | RA Ministry of Justice RA Ministry of Defense |  |  | Audit of the number of servants fulfilling functions, reserved for Police troops has been completed and submitted to the RA Prime Minister’s Staff. Baseline 0; In 2022 - 1 | Funding is not required. |  |  |  |  |  |  |  |  |  |
| 4 | Training of the National Guard, with a focus on the modern tactics for public order protection and professional abilities to conduct analytical projections |  |  | Second semester | First and second semesters |  |  | RA Ministry of Justice RA Ministry of Finance |  |  | Police troops have been trained to apply modern tactics for the protection of public order. Baseline 0; in 2022 at least 30% | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| Direction: Development of Criminal Police Problem: Artificial minimization of the role of the Police in responding to criminal cases and criminal investigating and inefficient use of resources. Target: Increase of the effectiveness of crime prevention and criminal investigation through more effective involvement of the criminal police |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Statistical analysis of the number of cases prepared by the Police and criminal cases |  |  | Second semester |  |  |  | RA Ministry of Justice |  |  | The study has been submitted to the Prime Minister’s Staff clarifying the scope of crimes that shall be investigated by the Police. | Funding is not required. |  |  |  |  |  |  |  |  |  |
| 2 | Introduction of the institution of detectives in the Police - Establishment preliminary investigation powers for the Police in the Criminal Procedure Code - Alignment of by-laws - Logistics of the service |  |  | Second semester | First and second semesters |  |  | RA Ministry of Justice RA General Prosecution RA Special Investigation Service RA Investigative Committee RA Ministry of Finance |  |  | Amendments have been introduced to ensure necessary legislative framework. New civil service positions to fulfil operative and investigative functions have been introduced to the Police. Feasibility study on introduction of the institute has been submitted to the RA Prime-Minister’s Staff Public discussion on amendments to the Criminal Procedure Code and their submission to the RA Prime-Minister’s Staff Baseline 0, In 2022 at least 1 public discussion, 30% of recommendations adopted. New positions with operative-investigative functions have been introduced within the system of police Baseline 0; in 2022 at least 50% positions | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 3. | Training of investigators of patrol service |  |  | First semester |  |  |  | RA Ministry of Justice |  |  | Patrol Service investigators have benefitted from 1 month training. Baseline 0; In 2022 at least 30 investigators |  |  |  |  |  |  |  |  |  |  |
| 4 . | Development of a methodology for investigating crimes |  |  | First semester |  |  |  | RA Ministry of Justice RA General Prosecution RA Special Investigation Service RA Investigative Committee RA Ministry of Finance |  |  | The international practice is studied. Criminal investigation methodology has been discussed with all stakeholders and submitted to the RA Prime-Minister’s staff Baseline 0; In 2022 - 1 | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 5 . | Creating a unified publicly available database of crimes that will contain classified data |  |  | First semester |  |  |  | RA Ministry of Justice RA General Prosecution RA Special Investigation Service RA Investigative Committee RA Ministry of Finance |  |  | The international practice in studied. Terms of Reference for creating the database is developed A unified public database of crimes has been introduced Baseline 0; In 2022 1 | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 6 . | Introduction of a comprehensive, unified electronic Registry of records on arrests of persons, which reflects all the stages and aspects of the process of arrests by the police, between actual detention of a person and transfer to another institution or release. |  |  | Second semester |  |  |  | RA Ministry of Justice RA General Prosecution RA Special Investigation Service RA Investigative Committee RA Ministry of Finance |  |  | Feasibility of introducing a comprehensive, unified electronic Registry has been studied and submitted to the RA Prime-Minister’s staff A comprehensive, unified electronic Registry of records on arrests of persons is introduced Baseline 0; in 2022 1 | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 7 . | Introduction of referral mechanism for persons reporting on acts of torture |  |  | Second semester |  |  |  | RA Ministry of Justice RA General Prosecution RA Special Investigation Service RA Investigative Committee RA Ministry of Finance Human Rights Defender (upon consent) |  |  | Feasibility of introducing a referral for persons reporting on acts of torture has been studied; The results have been submitted to the RA Prime-Minister’s staff Draft legislative amendments have been discussed and submitted to the RA Prime-Minister’s staff Baseline O; In 2022թ. Al least 1 discussion, at least 30% of recommendations are approved | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| Direction: Reconceptualization of community police Problem: Fulfillment of functions by community police that are not relevant to the institution and are typical of other bodies Target: Making of community police in the functional sense |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  | Funding is not required. |  |  |  |  |  |  |  |  |  |
| 1 | Functional and legislative audit of community police departments |  |  | First semester |  |  |  | RA Ministry of Justice RA Ministry of Labour and Social Affairs |  |  | The results of audit on community police officers’ operation and suggested revisions have been submitted to the RA Prime Minister’s Staff. | Funding is not required. |  |  |  |  |  |  |  |  |  |
| 2 | Fulfillment of community police functions by the Patrol service of the Police - Development of necessary legislative framework, approval and implementation of educational programs |  |  | Second semester | First semester |  |  | RA Ministry of Justice RA Ministry of Finance |  |  | Patrol police officer is performing the functions of community police. Results of feasibility study on fulfillment of community police functions by the Patrol service of the Police have been submitted to the RA Prime-Minister’s staff Draft legislative amendments have been submitted to the RA Prime-Minister’s staff Training programs for Community police have been reconsidered, in view of European best standards The servants fulfilling the functions community police benefitted from a special training program Baseline 0; In 2022 at least 30% of servicemen | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| Direction: Implementation of Police reform and international cooperation Problem: Limited participation/membership/cooperation of the police on international platforms, insufficient level of the international image and international rating of the police Target: Increase in the level of trust in the Armenian Police according to Caucasus Barometer surveys Baseline in 2017 - 29% (gross indicator of total and partial trust), target set for 2023 – 40% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Campaigns, aiming at the improvement of police’s international image and the new police profile | First semester Second semester |  | First semester Second semester |  |  |  | RA Ministry of Justice RA Ministry of Finance |  |  | The campaign has been carried out. Baseline 0; In 2021at least 6% of Police officers have been informed about the vision of the new police In 2021 at least 2 short training and informative video about patrol service and OMC In 2022 at least 10 TV programs and public debates | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 2 | Activating cooperation with Europol and EuroJust | First semester Second semester |  |  |  |  |  | RA Ministry of Justice RA Ministry of Foreign Affairs RA Ministry of Finance |  |  | The legal framework for cooperation with Europol has been signed. Negotiations on a cooperation agreement with EuroJust have been launched. Baseline 0; In 2022թ at least 3 high profile meeting with international partners | Funds allocated by the state budget, as well as means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 3 | Involvement of international partners in the reform process | First semester Second semester |  | First semester Second semester | First semester Second semester |  |  | RA Ministry of Justice |  |  | Reforms are being implemented with a systemic involvement of international partners. | Funding is not required. |  |  |  |  |  |  |  |  |  |
| Direction: Inclusiveness of reforms implementation, monitoring and coordination of activities Problem: Lack of a comprehensive system for monitoring and coordination of Police’s activity, existence of non-participatory and inclusive processes Target: Proper coordination of the multi-stakeholder Council monitoring and assessing the implementation of reforms |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Formation of an interdepartmental working group on police reforms | First semester |  |  |  |  |  | RA Ministry of Justice |  |  | An interdepartmental group for the development and implementation of police reforms has been set up. Baseline 0; In 2022 1 | Funding is not required. |  |  |  |  |  |  |  |  |  |
| 2 | Formation of the Coordination Council for the development and implementation of Police reforms | First semester |  |  |  |  |  | RA Ministry of Justice |  |  | Coordination Council for the development and implementation of Police reforms has been formed Baseline 0; in 2022 1 The Coordination Council held at least 4 meetings | Funding is not required. |  |  |  |  |  |  |  |  |  |
| 3 | Development of a methodology for conducting regular surveys on the level of public trust and the impact of measures, taken by the police | Second semester |  |  |  |  |  | RA Ministry of Justice |  |  | The methodology for conducting regular surveys on the level of public trust and the impact of measures, taken by the police has been developed. Baseline 0; In 2022 1 | Means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 4 | Conducting regular surveys on the level of public confidence and the impact of measures, taken by the police |  |  | First semester Second semester | First semester Second semester |  |  | RA Ministry of Justice |  |  | At least 1 public opinion poll on Police reform and implemented measures per year. | Means not prohibited by law. |  |  |  |  |  |  |  |  |  |
| 5 | Submission of six-month reports on the progress of reforms to the Council | Second six-month period |  | First semester Second semester | First semester Second semester |  |  | RA Ministry of Justice |  |  | Publishing at least 5 reports on Police reforms and implemented measures have been | Funding is not required. |  |  |  |  |  |  |  |  |  |
| Direction: Strategic communication Problem: problems with trust in and public opinion about the Police Target: Positive change of attitude to the police by means of reforms, namely through the recruitment of human resources with a high level of professionalism and right values and improvement of service quality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Development and implementation of strategic communication on reforms | First semester |  |  |  |  |  | RA Ministry of Justice |  | The Strategic Communication Program has been developed and submitted to the RA Prime Minister's Staff. Baseline 0; In 2022 1 |  |  |  | Means not prohibited by law. |  |  |  |  |  |  |  |
|  |  | First semester Second semester |  |  |  |  |  | RA Ministry of Justice |  | Implementation of a communication campaign on the introduction of the patrol service (with a focus on the patrol service in Yerevan and then in the marzes) Baseline 0; In 2020 60% of police officers are aware of new police vision In 2020 at least 2 short instructional and informative videos about patrol service և OMC, In 2020, at least 300 new staff members have applied to jobs within the patrol service In 2021, at least 10 TV programs and public debates, including through regional televisions. |  |  |  |  |  |  |  |  |  |  |  |

http://reports.weforum.org/global-competitiveness-index-2017-2018/competitiveness-rankings/#series=EOSQ055

The more detailed action plan for the creation of the service shall be approved.